# SSA AI Innovation Hub (iHub) 75-Day Rollout Plan

Version: vA
Date: January 2026
Status: DRAFT

## Executive Summary

SSA & Co. is launching a firm-wide AI Innovation Hub (iHub) to transform consulting capabilities through strategic AI adoption—encompassing both Generative AI and traditional ML disciplines including classification, simulation, and predictive modeling. This 75-day rollout plan delivers a company-wide implementation—not a pilot—executed through agile sprints with all workstreams running in parallel from Day 1.

The plan targets every SSA & Co. consultant, from Business Analysts to Managing Partners, building on the firm's "Business-Led, Data-Native, AI-First (but not AI-Only), and Human-Always" philosophy and Six Sigma heritage. Through disciplined sprint execution and clear milestones, SSA & Co. will achieve measurable productivity gains, elevated client value delivery, and sustainable competitive advantage.

Potential Target Outcomes:

- 80%+ firmwide active AI usage (GenAI + traditional ML) by Day 75

- 20%+ productivity improvement on routine tasks (consultant productivity)

- 80%+ projects utilizing published agents and/or ML models

- 40%+ acceleration in research-intensive work (time vs. effort)

- Fully operational 3-2-1 Support Framework

- Self-sustaining power user network across all practice areas

- Performance KPIs and metrics to articulate business impact

## Rollout Structure

### Sprint Architecture

| Sprint | Days | Focus Theme |
| --- | --- | --- |
| Sprint 0 | Days 1-5 | Foundation & Launch |
| Sprint 1 | Days 6-19 | Activation |
| Sprint 2 | Days 20-33 | Acceleration |
| Sprint 3 | Days 34-47 | Expansion |
| Sprint 4 | Days 48-61 | Optimization |
| Sprint 5 | Days 62-75 | Institutionalization |

### Parallel Workstreams

All seven workstreams execute concurrently throughout the rollout:

- Training & Enablement — Building firm-wide AI capabilities

- Governance & Infrastructure — Establishing secure, scalable foundations

- Support Systems & Community — Creating the 3-2-1 support ecosystem

- Use Case Development — Deploying high-value applications

- Client Development Support — Augmenting SKUs, sales, and marketing

- Impact Measurement & Analytics — Defining, tracking, and reporting KPIs

- Communications & Change — Driving adoption through engagement

## Workstream Summaries

### 1. Training & Enablement

Objective: Build firm-wide AI capabilities from foundational literacy to advanced specialization.

Key Deliverables:

- Skills Matrix updated with AI competencies (GenAI and traditional ML)

- Foundational training delivered to 100% of firm (2-hour sessions by practice)

- "ML for Consultants" module: when to apply classification, prediction, and simulation

- "Predictive Analytics for Consulting" and "Simulation & Scenario Modeling" workshops

- GenAI Certification program with 40%+ firm completion target

- Advanced ML track: model interpretation, feature engineering, AutoML workflows

- AI usage integrated into performance review criteria by Day 75

### 2. Governance & Infrastructure

Objective: Establish secure, scalable foundations with clear policies and development standards.

Key Deliverables:

- Enterprise license provisioning (Claude, Copilot, DataRobot)

- AI Usage Policy v1.0 covering GenAI and traditional ML

- Agentic development lifecycle (ideation → design → build → test → deploy → monitor → iterate)

- ML model governance framework (validation, drift monitoring, retraining triggers)

- Client data handling protocols and output quality standards

- Transition from "control" to "enablement" governance model

- Quarterly policy review cycle institutionalized

### 3. Support Systems & Community

Objective: Create the 3-2-1 support ecosystem enabling self-sufficiency.

3-2-1 Framework:

- 3 Channels: Self-Service (60%), Peer Support (30%), Hands-On (10%)

- 2 Types: Proactive (Gold Nuggets, workshops, Innovation Labs) and Reactive (ticketing, escalation)

- 1 Unified Intake: Single form with 24-hour SLA

Key Deliverables:

- AI Knowledge Hub on Resource Hub with Prompt Library (100+ templates)

- AI Buddy System pairings firm-wide

- Office Hours (1x/week minimum), expanding to practice-specific sessions

- Power User network (2+ per practice) with certification program

- AI Concierge Service and Emergency Hotline for complex/urgent needs

### 4. Use Case Development

Objective: Deploy high-value GenAI agents and traditional ML models across practices.

GenAI Agents:

- 5 priority agents deployed in Sprint 0; 25+ use cases by Day 75

- Practice-specific applications (Insurance, PE, Manufacturing, Operations)

- Knowledge management: vector search, methodology access, cross-project synthesis

Traditional ML Models:

- Classification: customer segmentation, risk scoring, fraud detection, defect identification

- Prediction: demand forecasting, churn prediction, capacity planning

- Simulation: Monte Carlo analysis, scenario planning, sensitivity analysis

Flagship: Process Reengineering Agent

- Multi-agent orchestrated system with 5 components: Data Ingestion, Process Mining, Analysis, Recommendation, Output Generation

- Human-in-the-loop checkpoints at each stage

- ML integration: classification for data categorization, clustering for pattern detection, prediction for impact estimation, simulation for scenario modeling

- Target: 50%+ time reduction vs. traditional process analysis; 80%+ adoption

### 5. Client Development Support

Objective: Augment SKUs, sales effectiveness, and marketing with AI capabilities.

Key Deliverables:

- GenAI messaging iterated within each practice and SKU

- AI-assisted proposal templates and competitive intelligence automation

- Client research and bio generation at scale

- Practice-specific AI value propositions for client conversations

- GenAI SKU offerings finalized with pricing guidance

- AI-enhanced pursuit prioritization and targeting

- Client development playbook published for all practices

- Win rate tracking: AI-enhanced proposals vs. baseline

### 6. Impact Measurement & Analytics

Objective: Define, track, and report KPIs demonstrating business value.

KPI Categories:

- Adoption: WAU, DAU, certification rates, power user density

- Productivity: Time savings by task type, cycle time reduction, capacity creation

- Quality: Deliverable scores, revision cycles, error rates

- Business Impact: Project margin, proposal win rate, CSAT, revenue per consultant

- Support Health: Ticket volume, resolution time, self-service rate, NPS

Key Deliverables:

- Baselines established in Sprint 0 (productivity, quality, cycle time, win rate, margin)

- GenAI Value Tracker dashboard with real-time data feeds

- Weekly adoption dashboards; monthly impact reports

- Mid-rollout and final ROI analyses delivered to leadership

- Quarterly business review cadence established

### 7. Communications & Change

Objective: Drive adoption through engagement, recognition, and transparent progress reporting.

Key Deliverables:

- Leadership launch message and "GenAI at SSA: What It Means for You" guide

- Weekly "AI Gold Nuggets" via Teams

- Practice-area-specific Teams channels for AI discussion

- "AI Wins" stories (30+ documented by Day 75)

- Firm-wide "GenAI Town Hall" in Sprint 3

- "State of GenAI at SSA" address in Sprint 5

- External thought leadership and success story compilation

## Sprint Execution Summary

### Sprint 0: Foundation & Launch (Days 1-5)

Objectives: iHub team activated, infrastructure ready, all-hands launch delivered.

| Workstream | Key Deliverables |
| --- | --- |
| Training | Skills Matrix updated; Week 1 sessions scheduled; pre-work distributed |
| Governance | Licenses provisioned; AI Usage Policy v1.0 published; agentic lifecycle established |
| Support | Knowledge Hub live; Prompt Library published; Office Hours scheduled |
| Use Cases | 5 agents deployed; ML model inventory complete; Process Reengineering Agent architecture documented |
| Client Dev | GenAI messaging drafted per practice/SKU |
| Measurement | KPI framework defined; baselines established; Value Tracker live |
| Communications | Launch message delivered; first Gold Nuggets sent |

✓ Day 5 Checkpoint: 100% access credentials, training scheduled, firm-wide awareness achieved.

### Sprint 1: Activation (Days 6-19)

Objectives: First training wave delivered, all practices using AI, support channels operational.

| Workstream | Key Deliverables |
| --- | --- |
| Training | Foundational training to 100% of firm; "ML for Consultants" module launched |
| Governance | Request tracking implemented; client data protocols published; lifecycle v1.1 |
| Support | Buddy System active; first Office Hours and Co-Creation Sessions held |
| Use Cases | 5 additional use cases; ML classification/forecasting templates; Process Agent alpha |
| Client Dev | AI-enhanced proposal metrics tracking initiated |
| Measurement | Time-savings capture launched; first weekly dashboard; first sentiment survey |
| Communications | 3+ "AI Wins" published; practice Teams channels launched |

✓ Day 19 Checkpoint: 50%+ trained, all practices active, support SLA operational.

### Sprint 2: Acceleration (Days 20-33)

Objectives: Majority using AI weekly, Power Users formalized, client value demonstrated.

| Workstream | Key Deliverables |
| --- | --- |
| Training | Advanced track launched; practice workshops; certification enrollment begins |
| Governance | 10+ playbooks published; first policy review cycle |
| Support | Power User network formalized; Innovation Labs launched |
| Use Cases | Practice-specific ML models (Insurance, PE, Ops); first custom agent; Process Agent beta/pilot |
| Client Dev | Practice-specific value propositions; first case study published |
| Measurement | First monthly impact report; project margin tracking; quality comparison initiated |
| Communications | Mid-rollout progress report; first certified users recognized |

✓ Day 33 Checkpoint: 65%+ WAU, Power Users designated, first custom agent deployed.

### Sprint 3: Expansion (Days 34-47)

Objectives: AI integrated into methodology, knowledge management transformed, cross-practice innovation.

| Workstream | Key Deliverables |
| --- | --- |
| Training | 30%+ certified; peer-led sessions; "Simulation & Scenario Modeling" training |
| Governance | Shared project accounts; citation requirements; mid-rollout security review |
| Support | AI Concierge Service launched; Emergency Hotline active; practice-specific Office Hours |
| Use Cases | Knowledge Hub vector search; Monte Carlo toolkit; Process Agent v1.0 firm-wide |
| Client Dev | GenAI SKU finalized; AI capability presentations; pursuit prioritization |
| Measurement | Mid-rollout ROI analysis; practice benchmarks; win rate tracking |
| Communications | First firm-wide Town Hall; 15+ success stories; competitive positioning launched |

✓ Day 47 Checkpoint: 75%+ WAU, 30%+ certified, knowledge management operational.

### Sprint 4: Optimization (Days 48-61)

Objectives: Clear ROI demonstrated, self-sustaining ecosystem, advanced capabilities deployed.

| Workstream | Key Deliverables |
| --- | --- |
| Training | "Bluesky GenAI" sessions; advanced ML track; second certification cohort |
| Governance | Enablement model; continuous monitoring; updated policies |
| Support | Health checks per practice; non-adopter support; 2+ Power Users/practice |
| Use Cases | Ensemble classification; time-series prediction; real-time simulation dashboards; Process Agent v1.1 + industry variants |
| Client Dev | Win rate analysis; SKU refinement; client development playbooks |
| Measurement | Comprehensive ROI report; productivity calculations finalized; executive dashboard |
| Communications | ROI analysis published; lessons learned; external thought leadership prepared |

✓ Day 61 Checkpoint: 80%+ WAU, 20%+ productivity improvement, advanced agents deployed.

### Sprint 5: Institutionalization (Days 62-75)

Objectives: AI embedded as business-as-usual, sustainable model in place, 2025 roadmap set.

| Workstream | Key Deliverables |
| --- | --- |
| Training | AI in performance reviews; Skills Matrix integration; 2025 capability plan |
| Governance | Cost optimization; quarterly review cycle; ML lifecycle governance finalized |
| Support | Steady-state model; Community governance; iHub 2.0 charter |
| Use Cases | Practice Cookbooks complete; ML model catalog; Process Agent in standard methodology |
| Client Dev | SKU catalog and playbook finalized; 2025 AI enhancement roadmap |
| Measurement | Final impact report; firm-wide benchmarks; 2025 targets; QBR cadence |
| Communications | "State of GenAI" address; success compilation; "AI Leaders" 2025 vision |

✓ Day 75 Checkpoint: All targets achieved, sustainable operating model, SSA positioned as AI-enabled leader.

## iHub Core Team

| Role | Name |
| --- | --- |
| iHub Lead | Nick Kramer |
| iHub Advisor | Pierre Buhler |
| Technical Excellence Lead | Mithun Kalaga |
| Prompt Engineering Lead | Ashok Talluri |
| GenAI & DataRobot Product Owner | Matt Derganc |
| GenAI & DataRobot Product Owner | Matthew Lee |
| Classic AI/ML Product Owner | Sean DiCarolis |
| (Gen)AI Development Lead | Patryk Mazinski |
| (Gen)AI Developer | Amanda Palamar |
| (Gen)AI Developer | Emory Wise |
| (Gen)AI Developer | Camp Hagood |
| Client Development SME | Melanie Goldsmith |

Extended Network: Power Users (2+ per practice), Practice Champions (1 per practice), Executive Sponsors

This executive summary reflects SSA & Co.'s commitment to Business-Led, Data-Native, AI-First (but not AI-Only), and Human-Always transformation.